## Project List 2021
2021 Arizona State Facilities Board
Project Listing
22 June 2021
Installation | City and State | Project Name | Approx. Fed Cost ($M) | State Share Cost ($M) | Date Recommended Mo. & Yr. | Program Year | Component Project Number | Project Remarks
Arizona Army National Guard (ARNG)
Rita Road MIF | Tucson, AZ | Readiness Center | 18.1 | 6 | 2015-01-15 | FY 21 | 040037 | Listed on FYDP, Environmental Assessment in process, Initial Design Authority received.
Surprise | Surprise, AZ | Readiness Center | 11.6 | 3.9 | 2012-08-01 | FY 23 | 040350 | Listed on FYDP, Finalizing Land Selection. Moved from FY 22 to FY 23
Rita Road MIF | Tucson, AZ | Field Maintenance Shop | 20 | N/A | 2018-06-04 | TBD | 040993
Florence Military Reservation (FMR) | Florence, AZ | Scout Recce Live Fire Range | 17 | N/A | 2021-05-19 | TBD
Florence Military Reservation (FMR) | Florence, AZ | FMS #4 add/alt | 4 | N/A | TBD | TBD
Arizona Air National Guard (AZ ANG)
Sky Harbor Airport (161st ARW) | Phoenix, AZ | Main Gate | 2.9 |  | TBD | TBD |  | O&M Project. Project on hold until base expansion COA determined
Sky Harbor Airport (161st ARW) | Phoenix, AZ | ADAL Airfield Expansion | 2.4 |  | 2021-11-21 | FY 22 | VTNB162484 | 100% plan completed June 2020. SRM funded from NGB/A4.
Sky Harbor Airport (161st ARW) | Phoenix, AZ | Lease Renewal/expansion of property | TBD / $200 |  | 1931-11-01 | FY 32 |  | COP Aviation Dept. approved Comprehensive Management Plan to relocate all cargo functions to the north side of airport. This will allow 161 ARW to expand the west to acquire 60 acre and current buildings used by FedEx/UPS. Funding source - TBD
Tucson Airport (162nd Wing) | Tucson, AZ | Main Gate (Land Acquisition) | 6 |  | 2014-03-01 | FY 22 | XHEA179047
Tucson Airport (162nd Wing) | Tucson, AZ | Main Gate (Construction) | 8 |  | 2014-03-01 | FY 24 | XHEA109012 | 35% design complete
Tucson Airport (162nd Wing) | Tucson, AZ | Munitions Storage Area | 22 |  | 2002-01-01 | FY 27 | XHEA029101 | 15% design complete
Tucson Airport (162nd Wing) | Tucson, AZ | Aircraft Arresting Systems (New Rwy) | 9.4 |  | 2021-01-18 | FY 23 | XHEA999163 | In design (MCCA with TAA)
U.S. Air Force Reserve (USAFR)
Davis Monthan AFB | Tucson, AZ | GAARV/Storage Facility | 5.4 |  | 2021-06-18 | FY 22-23 | FBNV203001
Davis Monthan AFB | Tucson, AZ | 924 Squad Ops 47 FS | 5.5 |  |  | FY 24 | FBNV141003 | Unilateral
Davis Monthan AFB | Tucson, AZ | Security Forces Facility | 5.4 |  |  | FY 26 | PDPG180107 | Unilateral
Davis Monthan AFB | Tucson, AZ | 610 CAC Admin Facility | 5.7 |  |  | FY 22 | FBNV19003 | Unilateral
Davis Monthan AFB | Tucson, AZ | Wing Facility | 12 |  | TBD |  |  | Non-Acqu - New mission in the future
U.S. Army Reserve (USAR)
Rittenhouse | Queen Creek, AZ | Construct AMSA-96 at Rittenhouse site | 12.4 |  | TBD | FY 25 | 89896 | Unilateral
Herrera Hall ARC | Mesa, AZ | Herrera Hall ARC/VMS Addition | TBD |  | TBD | FY 23-24 | 97908 | Unilateral
Herrera Hall ARC | Mesa, AZ | Military Equipment Park (MEP) Expansion + Repave | 2.7 |  | TBD | FY 23-24 | 97888 | Unilateral
ARNG/USAR Center | Marana, AZ | Military Equipment Park (MEP) Expansion + Repave | TBD |  | TBD | TBD | TBD | Unilateral
Buckeye ARC | Buckeye, AZ | ARC and VMS additions MEP Expansion | TBD |  | TBD | TBD | TBD | Unilateral
U.S. Marine Corp Reserve (USMCR)
No new projects at this time
U.S. Naval Reserve (USNR)
No new projects at this time

## Project Tally 2021
2021 AZ SFB
| Projects | Joint | Unilateral
USAR | 5 | 0 | 5
USAFR | 5 | 0 | 5
AZ ANG | 7 | 0 | 7
AZ ARNG | 5 | 0 | 5
USNR | 0 | 0 | 0
USMCR | 0 | 0 | 0
| 22 | 0 | 22