## Opportunity Report
P2# | Project Type | Opportunity | Project Description | Location | Feature | Task Name / Activity Name | Category | Design By Desc | Authorized Phase Code | Authorized Phase Desc | Ready to Advertise (ML180) | Directed Amount | Acquisition Strategy | Solicitation Type | Business Line
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel North Phase 1 - Section A, Section B, and Plug A (Partial) | BCN - 1 BIL E&D DURING CONSTRUCTION (EXERCISE OPTION ON SOLE SOURCE CONTRACT) | AE |  |  |  | FY26 Q4 | $1 – 5M | NONE / No set aside used | OCMN / Non-Competitive Other Contracting Method | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel North Phase 1 Rec - Section A, Section B, and Plug A (Partial) | BCN - 1 BIL PED BRIDGE CONTRACT (FED REC) | Construction |  |  |  | FY26 Q4 | $5 – 10M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel North Phase 1 Rec - Section A, Section B, and Plug A (Partial) | BCN - 1 BIL PED BRIDGE CONTRACT (NON-FED REC) | Construction |  |  |  | FY26 Q4 | $5 – 10M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel South Phase 1 | BCS - 1 BIL CONTRACT | Construction |  |  |  | FY27 Q3 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel South Phase 1 | BCS - 1 CONTRACT (NON-FED) | Construction |  |  |  | FY27 Q3 | $25 – 50M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel South Phase 1 Rec | BCS - 1 BIL PED BRIDGE CONTRACT (FED REC) | Construction |  |  |  | FY27 Q3 | $5 – 10M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Bypass Channel South Phase 1 Rec | BCS - 1 BIL PED BRIDGE CONTRACT (NON-FED REC) | Construction |  |  |  | FY27 Q3 | $5 – 10M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | RW / UD - AE Final Design | RU BIL AE CONTRACT - FINAL DESIGN (BETTERMENTS) | AE |  |  |  | FY26 Q3 | < $1M |  |  | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | Samuels Ave & M.C. Dam & M.C. Channel Expansion | SAM-MC INTERMEDIATE P&S & DDR SAR A-E TASK ORDER | AE |  |  |  | FY27 Q2 | < $1M | NONE / No set aside used | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | SAM-MC AE - 100% | SAM-MC AE TASK ORDER (FINAL DESIGN) IIJA | AE |  |  |  | FY26 Q4 | $10 – 25M | NONE / No set aside used | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
100573 | Civil Works | Central City, UTRB, CON | 081525 Central City, Upper Trinity River Basin, Fort Worth Tarrant Regional Water District, TX, Flood and Coastal Storm Damage Reduction - Construction | CENTRAL CITY, FORT WORTH, UPPER TRINITY RIVER BASIN, TX | SAM-MC AE - 100% | SAM-MC AE TASK ORDER (FINAL DESIGN) IIJA-R | AE |  |  |  | FY26 Q4 | $10 – 25M | NONE / No set aside used | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
354571 | Civil Works | CW (Sandbox) | Blank Sandbox for Future Use | Coordination With Other Water Resources Agencies |  | CONTRACT | Construction |  |  |  | FY28 Q1 | $25 – 50M | NONE / No set aside used | RFP2 / RFP - Two Step | CIVIL NonCAP
450634 | Military | CAP 081422 JBSA Ambulatory Care Center, Ph 4 | Construct Ambulatory Care Center, Ph 4 | Joint Base San Antonio | Construction | CONSTRUCTION CONTRACT (SEE NOTEBOOK - GENERAL NOTES) | Construction | Architect-Engineer | 6 | Final Design | FY26 Q4 | $50 – 100M |  |  | OTHER MILCON CAPCES
456277 | Military | ACE MPLS220527 JBSA BMT Sat Classrooms/Dining Fac 4 | Construct ATC Dining-Classroom Facility 4, Lackland | Lackland Air Force Base | Construction | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY26 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
456279 | Military | ACE MPLS083737 JBSA BMT RECRUIT DORMITORY 6 | Construct ATC Dormitory 6 | Joint Base San Antonio | S1!CX#SWF3960312<NULL>NULL | SB - CONTRACT | Construction | Architect-Engineer | 9 | Construction Contract Award Authorized | FY27 Q3 | $10 – 25M | 8a / 8(a) | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
456499 | Civil Works | CAP - River Road, SARA, TX Sec 206 | Aquatic Ecosystem Restoration along San Antionio River within San Antonio, TX | RIVER ROAD, SARA, TX (CAP SEC 206) |  | RIVER ROAD BIL A-E TASK ORDER (NFS BETTERMENTS) | AE |  |  |  | FY26 Q3 | < $1M | NONE / No set aside used | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL CAP
456499 | Civil Works | CAP - River Road, SARA, TX Sec 206 | Aquatic Ecosystem Restoration along San Antionio River within San Antonio, TX | RIVER ROAD, SARA, TX (CAP SEC 206) |  | RIVER ROAD BIL CONTRACT - ER | Construction |  |  |  | FY27 Q3 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL CAP
456499 | Civil Works | CAP - River Road, SARA, TX Sec 206 | Aquatic Ecosystem Restoration along San Antionio River within San Antonio, TX | RIVER ROAD, SARA, TX (CAP SEC 206) |  | RIVER ROAD BIL CONTRACT - REC | Construction |  |  |  | FY27 Q3 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL CAP
463770 | Military | CAP 076629 JBSA Laboratory Instructional Building | Construct Laboratory Instructional Building | Joint Base San Antonio | VMP Update | CONTRACT - | Construction | Design-Build, RFP developed by A-E | 2 | Concept Design | FY28 Q1 | $50 – 100M | SB / Small Business | RFP2 / RFP - Two Step | MAJOR MILCON CAPCES
468759 | Civil Works | Dallas Floodway - FRM Elements - BBA 2018 | Levee Raise, Levee Slope Flattening, Pump Station Construction and AT&SF Bridge Modification | DALLAS FLOODWAY, UPPER TRINITY RIVER BASIN, TX | 6.1) DF Trinity Portland PS 2 | DF TP PS-2 CONTRACT | Construction |  |  |  | FY28 Q1 | $100 – 250M | NONE / No set aside used | RFP2 / RFP - Two Step | CIVIL NonCAP
468759 | Civil Works | Dallas Floodway - FRM Elements - BBA 2018 | Levee Raise, Levee Slope Flattening, Pump Station Construction and AT&SF Bridge Modification | DALLAS FLOODWAY, UPPER TRINITY RIVER BASIN, TX | 7) DF Hampton PS | DF HAMPTON CONTRACT | Construction |  |  |  | FY27 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
472496 | Military | ACE MPYJ043895A Lackland Aquatics Tank | Aquatics Tank, Lackland | Lackland Air Force Base | Construction | CONSTRUCTION CONTRACT (SEE NOTEBOOK - GENERAL NOTES) | Construction | Architect-Engineer | 9 | Construction Contract Award Authorized | FY27 Q1 | < $1M |  |  | MAJOR MILCON ACES
472820 | Military | ACE MPLS083006 JBSA Chapel for America's Airman | Construct Chapel for America's Airmen, Lackland | Lackland Air Force Base | P1!CX#NULL<NULL>NULL | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
472866 | Military | ACE MPLS163002 JBSA CNS 91 Cyber Operations Center | Construct Cyber Operations Center, Lackland | Lackland Air Force Base | Construction | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q4 | > $250M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON ACES
473846 | Military | Barksdale Renovate Corrosion Control Hangar Blg 6626 | Barksdale Renovate Corrosion Control Hangar Blg 6626 | Barksdale Air Force Base |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY26 Q4 | $100 – 250M | 8a / 8(a) | RFP1N / Non-Competitive RFP - One Step | MILITARY SRM
476460 | Civil Works | Dallas Floodway Extension - BBA 2018 | New Levee Construction | DALLAS FLOODWAY EXTENSION, TRINITY RIVER PROJECT, TX | 1) DFE Lamar Levee | DFE LAMAR LEVEE CONTRACT | Construction |  |  |  | FY28 Q1 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
476460 | Civil Works | Dallas Floodway Extension - BBA 2018 | New Levee Construction | DALLAS FLOODWAY EXTENSION, TRINITY RIVER PROJECT, TX | 1) DFE Lamar Levee | DFE LAMAR LEVEE CPS CONTRACT | AE |  |  |  | FY28 Q1 | $1 – 5M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
476460 | Civil Works | Dallas Floodway Extension - BBA 2018 | New Levee Construction | DALLAS FLOODWAY EXTENSION, TRINITY RIVER PROJECT, TX | 2) DFE Cadillac Heights Levee | DFE CH CPS CONTRACT | AE |  |  |  | FY28 Q1 | $1 – 5M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
476460 | Civil Works | Dallas Floodway Extension - BBA 2018 | New Levee Construction | DALLAS FLOODWAY EXTENSION, TRINITY RIVER PROJECT, TX | 2) DFE Cadillac Heights Levee | DFE CH LEVEE CONTRACT | Construction |  |  |  | FY28 Q1 | $100 – 250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
476460 | Civil Works | Dallas Floodway Extension - BBA 2018 | New Levee Construction | DALLAS FLOODWAY EXTENSION, TRINITY RIVER PROJECT, TX |  | RESTORATION | Services |  |  |  | FY28 Q1 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL NonCAP
477047 | Environmental | K06TX030409 CAMP SWIFT: MRS 9 | CAMP SWIFT: MRS 9 Main Artillery Range and IA/BZ | Camp Swift | RA-C | RAC CONTRACT: | Services |  |  |  | FY27 Q4 | $25 – 50M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
483256 | Military | CAP 093735 JBSA Applied Instruction Building | Construct Applied Instruction Building, Camp Bullis | Joint Base San Antonio | Construction | DB CONTRACT | Construction | Design-Build, RFP developed by Hired Labor | A | Authority to Advertise | FY26 Q4 | $25 – 50M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | OTHER MILCON CAPCES
485699 | Environmental | FY20 AF Project Funding | FY20 projects for the Air Force | Joint Base San Antonio |  | CONTRACT: | Services |  |  |  | FY26 Q3 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
494479 | Environmental | FY21 RD-Readiness Division | FY21 projects for the RD | Var Conus |  | CONTRACT: | Services |  |  |  | FY26 Q4 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
498065 | IIS | Dallas VA Clinical Expansion for Mental Health (CEMH) | Build a new VA Mental Health Clinical Expansion in Dallas, Texas | Dallas, Tx |  | PARKING GARAGE ASBESTOS CONTRACT | Construction | Design-Build, RFP developed by A-E | 9 | Construction Contract Award Authorized | FY27 Q2 | $1 – 5M |  |  | IIS
499890 | Civil Works | Proctor Dam - Dam Safety Modification | Proctor Dam is currently a DSAC 3 based on the DSMS completed in APR 21 ? HQUSACE approved the DSMR and completion of long-term risk reduction efforts via DSM in JUL 21 | PROCTOR LAKE, TX |  | CONSTRUCTION CONTRACT | Construction |  |  |  | FY27 Q1 | $25 – 50M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | CIVIL NonCAP
500537 | Military | ACE JCGU133001 Goodfellow Pipeline Student Dormitory | Pipeline Student Dormitory | Goodfellow Air Force Base |  | CONTRACT | Construction | Design-Build, RFP developed by A-E | A | Authority to Advertise | FY27 Q1 | > $250M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON ACES
503071 | Civil Works | CF Whitney PH SCADA Sys Inst | Installation of a SCADA System at Whitney Powerplant. | Whitney Lake, TX |  | CONTRACT - WH SCADA NF$ ($825K) | Construction |  |  |  | FY27 Q2 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | CIVIL O&M
504196 | Military | ACES TYMX180214 JBSA Add/Alter T-7A Egress Facility, B38 | ACES TYMX180214 Add/Alter T-7A Egress Facility, B38 | Joint Base San Antonio |  | CONTRACT | Construction | Architect-Engineer | A | Authority to Advertise | FY26 Q4 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON ACES
504198 | Military | ACES MXDP193004 Laughlin T-7A Hush House Pad | ACES MXDP193004 T-7A Hush House Pad | Laughlin Air Force Base |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON ACES
504238 | Military | ACES MXDP213002 Laughlin T-7A Sunshade Allied Support | ACES MXDP213002 T-7A Sunshade Allied Support | Laughlin Air Force Base |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | $5 – 10M | SB / Small Business | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
504239 | Military | ACES MXDP213001 Laughlin T-7A Egress Shop Addition | ACES MXDP213001 T-7A Egress Shop Addition | Laughlin Air Force Base |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q2 | $5 – 10M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON ACES
505214 | Military | ACE JBSF200567 JBSA Construct METC Dorm #1 | ACE JBSF200567 JBSA Construct METC Dorm #1 | Joint Base San Antonio |  | DESIGN-BUILD CONTRACT | Construction | Design-Build, RFP developed by Hired Labor | 7 | Design Build | FY27 Q4 | > $250M | NONE / No set aside used | RFP2 / RFP - Two Step | MAJOR MILCON ACES
506597 | Civil Works | CF Sam Rayburn PH Generator Uprate/Rewind | Replacement of the generator rewind with a potental to uprate at the Sam Rayburn Powerhouse. | Sam Rayburn Dam and Reservoir, TX |  | CONTRACT - [CONTRACT NUMBER] - GENERATOR REWIND | Construction |  |  |  | FY28 Q4 | $100 – 250M |  |  | CIVIL O&M
507485 | Military | ACE FNWZ220040 Dyess B-21: Util & Site Improvements (Comms) | B-21: Utilities & Site Improvements (Comms) | Dyess AFB, TX |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | $25 – 50M | SB / Small Business | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
507486 | Military | ACE FNWZ213007 B-21: Low Observable/Radio Frequency Hangar | B-21: Low Observable/Radio Frequency Hangar | Dyess AFB, TX |  | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
507520 | Military | ACE FNWZ213012 Dyess B-21: MISSION PLANNING FAC | B-21: MISSION PLANNING FACILITY | Dyess AFB, TX |  | CONTRACT | Construction | Architect-Engineer | A | Authority to Advertise | FY27 Q1 | $100 – 250M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON ACES
511427 | Military | CAP 75644 Bliss Collective Training Barracks BN2 | CAP 75644 Bliss Collective Training Barracks | Fort Bliss | Construction | CONSTRUCTION CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
511428 | Military | CAP 100948 Hood Barracks #103 | CAP 100948 Hood Barracks | Fort Hood |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
511429 | Military | CAP 96800 Bliss Shipping and Receiving Building | CAP 96800 Bliss Shipping and Receiving Building | Fort Bliss |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Hired Labor - In House | 6 | Final Design | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON CAPCES
511429 | Military | CAP 96800 Bliss Shipping and Receiving Building | CAP 96800 Bliss Shipping and Receiving Building | Fort Bliss |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q3 | $50 – 100M | SB / Small Business | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
511493 | Military | CAP 94937 Hood Barracks #104 | CAP 94937 Hood Barracks | Fort Hood |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Hired Labor - In House | 6 | Final Design | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON CAPCES
511493 | Military | CAP 94937 Hood Barracks #104 | CAP 94937 Hood Barracks | Fort Hood |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
511669 | Military | Barksdale AFB Repair B6413 Secure Space | Barksdale AFB Repair B6413 | Barksdale Air Force Base | Construction | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $50 – 100M | 8a / 8(a) | RFP1N / Non-Competitive RFP - One Step | MILITARY SRM
512513 | Military | ACE FNWZ213009 Dyess B-21 FLIGHT SIMULATOR FACILITY | B-21 FLIGHT SIMULATOR FACILITY | Dyess AFB, TX | Construction | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | $100 – 250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
513057 | Military | CAP 092372 Bliss Intelligence Coordination Annex | Intelligence Coordination Annex | Fort Bliss |  | CONSTRUCTION CONTRACT | Construction | Design-Build, RFP developed by A-E | 9 | Construction Contract Award Authorized | FY26 Q3 | $10 – 25M | SB / Small Business | RFP2 / RFP - Two Step | MINOR MILCON CAPCES
513132 | Military | CAP 092186 Hood Vehicle Maintenance Shop #71 | Vehicle Maintenance Shop #71 | Fort Hood | Construction | CONSTRUCTION CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q1 | $100 – 250M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON CAPCES
513337 | Military | CAP 100994 Hood Barracks #105 | Barracks | Fort Hood |  | CONTRACT | Construction | Hired Labor - In House | 2 | Concept Design | FY28 Q3 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
513338 | Military | CAP 075646 Bliss Collective Training Barracks BN3 | Collective Training Barracks | Fort Bliss |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q3 | $100 – 250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
513841 | Military | Bliss Level II EV Charging Station | Bliss Level II EV Charging Station | Fort Bliss |  | AE MOD TASK ORDER | AE | Non-Construction | 6 | Final Design | FY26 Q3 | < $1M | SB / Small Business | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
513842 | Military | Bliss B11685 HVAC Repairs | Bliss-HVAC Repairs | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MILITARY SRM
513843 | Military | Bliss (FE104786J) B21 Floor Replacement | Bliss-Building Repairs | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $1 – 5M | SB / Small Business | RFP1 / Competitive RFP - One Step | MILITARY SRM
514094 | Military | ACE JCGU185001 Goodfellow Jacobson Gate Entry Control Point | Jacobson Gate Entry Control Point | Goodfellow Air Force Base | Goodfellow | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON ACES
514340 | Military | Bliss B11108 Hangar Repair | Bliss Bldg 11108 Hangar Repair DESIGN ONLY | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 7 | Design Build | FY27 Q1 | $25 – 50M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
515196 | Environmental | Altus/Little Rock AFBS F2F FY24 Acquisition | Acquisiiton of Fence-to-Fence (F2F) Environmental Services Contract for Altus Air Force Base, Oklahoma and Little Rock Air Force Base, Arkansas (3 year contract) - Labor Only | Fort Worth, Tx | OY2 | OPTION YEAR 2 CONTRACT | Services |  |  |  | FY26 Q4 | $1 – 5M | NONE / No set aside used | IDCN / Non-Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
515212 | Military | Barksdale AFB Repair B5546 Crisis Action Center | Barksdale AFB Repair B5546 Crisis Action Center | Barksdale Air Force Base |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q4 | $25 – 50M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
516387 | Military | CAP 103591 JBSA Upgrade Critical Medical Facilities | Upgrade Critical Medical Facilities | Joint Base San Antonio | Construction | CONTRACT | Construction | Design-Build, RFP developed by A-E | 7 | Design Build | FY28 Q1 | $100 – 250M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | OTHER MILCON CAPCES
516566 | Military | CAP 095536 HOOD STAGING/MARSHALLING AREA | Staging/Marshalling Area | Fort Hood |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
517079 | Military | ACE MXDP153002 Laughlin Const Drainage, Arizona & Liberty | ACE MXDP153002 Laughlin Construct Drainage, Arizona & Libert | Laughlin Air Force Base |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY28 Q4 | $5 – 10M | SB / Small Business | RFP1N / Non-Competitive RFP - One Step | MINOR MILCON ACES
517103 | Military | ACE FNWZ213006 Dyess Weapons Generation Facility | ACE FNWZ213006 Weapons Generation Facility | Dyess AFB, TX | Construction | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY28 Q4 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
517896 | Military | CAP 078303 Hood Military Working Dog (MWD) Kennel | Military Working Dog (MWD) Kennel | Fort Hood |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
517916 | Military | ACE KELL203614 Multi-Domain CYBER and Intel OPERATIONS | ACE KELL203614 Multi-Domain CYBER and Intel OPERATIONS | Lackland Air Force Base |  | AE DB TASK ORDER | AE | Architect-Engineer | 7 | Design Build | FY26 Q3 | $10 – 25M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON ACES
519426 | Military | BLISS (FE101981J) REPAIR ELLERTHORPE RD | Repair Ellerthorpe RD, FE 10198 1J | Fort Bliss |  | CONSTRUCTION PHASE SERVICES - ELLERTHORPE ROAD REPAIRS | AE | Architect-Engineer | 9 | Construction Contract Award Authorized | FY26 Q3 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
519428 | Military | BLISS (FE100371J) Repair Sergeant Major Blvd | BLISS (FE100371J) Repair Sergeant Major Blvd | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MILITARY SRM
519539 | Military | Bliss (DES101822P) Apparatus Bay B11211 | Bliss (DES101822P) Apparatus Bay B11211 | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY26 Q4 | $5 – 10M | 8a / 8(a) | RFP1 / Competitive RFP - One Step | MILITARY SRM
519580 | Military | Barksdale AFB Repair B6413 Second Floor Secure Space | Barksdale AFB Repair B6413 Secure Space | Barksdale Air Force Base | Construction | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q1 | $25 – 50M | 8a / 8(a) | RFP1N / Non-Competitive RFP - One Step | MILITARY SRM
520249 | Military | CAP 061075 RRAD Non-Destructive Testing Facility | Non-Destructive Testing Facility | Red River Army Depot |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q4 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
520250 | Military | CAP 097031 RRAD Standby Generator | Standby Generator | Red River Army Depot |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q3 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
520256 | Military | CAP 100540 RRAD Climate Controlled Storage Facility | Controlled Humidity Warehouse, Depot Level | Red River Army Depot |  | CONTRACT | Construction | Hired Labor - In House | 6 | Final Design | FY26 Q4 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
521132 | Military | OTH 105529 Hood Central Energy Plant | Hood Central Energy Plant | Fort Hood |  | CONSTRUCTION CONTRACT | Construction | Hired Labor - In House | A | Authority to Advertise | FY27 Q1 | $50 – 100M | SB / Small Business | RFP1 / Competitive RFP - One Step | OTHER MILCON CAPCES
521147 | Environmental | Fort Chaffee Building 460 Compliance Sampling | Installation and quarterly sampling of three new groundwater monitoring wells near building 460 at Fort Chaffee | Fort Chaffee |  | CONTRACT ACTIVITY (OPTION YEAR 3) | Services |  |  |  | FY27 Q4 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
521147 | Environmental | Fort Chaffee Building 460 Compliance Sampling | Installation and quarterly sampling of three new groundwater monitoring wells near building 460 at Fort Chaffee | Fort Chaffee |  | CONTRACT ACTIVITY (OPTION YEAR 4) | Services |  |  |  | FY28 Q4 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
521231 | Military | CAP 105154 Polk Instrument Landing System | Instrument Landing System | Fort Polk | AE Contract 2 | 100% DESIGN AE TASK ORDER - | AE | Architect-Engineer | 6 | Final Design | FY26 Q3 | $10 – 25M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON CAPCES
521231 | Military | CAP 105154 Polk Instrument Landing System | Instrument Landing System | Fort Polk | Construction | CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | $10 – 25M | SB / Small Business | RFP1 / Competitive RFP - One Step | MINOR MILCON CAPCES
521232 | Military | CAP 102842 Polk Animal Building | Animal Building | Fort Polk |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Design-Build, RFP developed by Hired Labor | A | Authority to Advertise | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON CAPCES
521232 | Military | CAP 102842 Polk Animal Building | Animal Building | Fort Polk |  | CONTRACT | Construction | Design-Build, RFP developed by Hired Labor | A | Authority to Advertise | FY27 Q1 | $10 – 25M | 8a / 8(a) | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON CAPCES
521233 | Military | JBSA 37 TRW DLIELC Repair HVAC B7437, 7445, 7447, 7535 | JBSA 37 TRW DLIELC HVAC Repair B7437, 7445, 7447, 7535 | Joint Base San Antonio | Construction | CONSTRUCTION CONTRACT - # (SEE NOTEBOOK - GENERAL NOTES) | Construction | Architect-Engineer | 6 | Final Design | FY27 Q4 | $5 – 10M | 8a / 8(a) | RFP1N / Non-Competitive RFP - One Step | MILITARY SRM
521703 | Military | ACE FNWZ243116 Dyess B-21 Util & Site Improvements Electric | B-21 Utilities Site Improvements Electric | Dyess AFB, TX |  | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY28 Q1 | $25 – 50M | SB / Small Business | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
521771 | IIS | DHS Border Wall Termination Settlement Proposals | DHS Border Wall Termination Settlement Proposals for RGV-02, RGV-04, RGV-06, RGV-07, RGV-08, RGV-09, RGV-10, Laredo North, and Laredo South | McAllen, Tx |  | SCHEDULING EXPERT CONTRACT | Services | Technical Services |  |  | FY26 Q3 | < $1M |  |  | IIS
521771 | IIS | DHS Border Wall Termination Settlement Proposals | DHS Border Wall Termination Settlement Proposals for RGV-02, RGV-04, RGV-06, RGV-07, RGV-08, RGV-09, RGV-10, Laredo North, and Laredo South | McAllen, Tx |  | SCHEDULING EXPERT CONTRACT | Services | Technical Services |  |  | FY26 Q3 | < $1M |  |  | IIS
521907 | Military | JBSA ARNORTH B4012 HVAC Renovation | JBSA ARNORTH B4012 HVAC Renovation | Joint Base San Antonio |  | CONSTRUCTION CONTRACT (SEE NOTEBOOK - GENERAL NOTES) | Construction | Architect-Engineer | 6 | Final Design | FY27 Q2 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
551464 | Military | CAP 073282 Hood Child Development Center (McNair) | CHILD DEVELOPMENT CENTER-UNDER 6 YEARS AGE | Fort Hood |  | AE CONTRACT | AE | Hired Labor - In House | 2 | Concept Design | FY28 Q2 | $1 – 5M |  |  | MAJOR MILCON CAPCES
551465 | Military | CAP 080281 Hood Child Development Center (Comanche) | CHILD DEVELOPMENT CENTER UNDER 6 YEARS AGE | Fort Hood |  | AE CONTRACT | AE | Hired Labor - In House | 2 | Concept Design | FY28 Q2 | $1 – 5M |  |  | MAJOR MILCON CAPCES
566141 | Military | BLISS (FE101492J) Repair B3672 Metal Roof | Metal roof in bldg. 3672 is in need of replacement due to severe wear and tear conditions. | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY27 Q2 | $10 – 25M | SB / Small Business | RFP1N / Non-Competitive RFP - One Step | MILITARY SRM
566251 | Military | CAP 096851 Bliss Dona Ana Base Camp Expansion | Dona Ana Base Camp Expansion | Fort Bliss | Construction | CONTRACT | Construction | Architect-Engineer | 2 | Concept Design | FY27 Q4 | $100 – 250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON CAPCES
566517 | Military | CAP 087812 Hood Barracks #107 | CAP 087812 Hood Barracks | Fort Hood |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Hired Labor - In House | 2 | Concept Design | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON CAPCES
566518 | Military | CAP 097218 Hood Barracks #106 | CAP 097218 Hood Barracks | Fort Hood |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Hired Labor - In House | 2 | Concept Design | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON CAPCES
566608 | Military | ACE MPYJ213587 CTA MILITARY WORKING DOG LARGE CAP KENNEL | MILITARY WORKING DOG LARGE CAPACITY KENNEL | Joint Base San Antonio | Construction | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY27 Q3 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
566936 | Military | Polk Repair TEMF, Building 4642 | Polk Repair TEMF, Building 4642 | Fort Polk | Construction | CONSTRUCTION CONTRACT - # | Construction | Hired Labor - In House | 7 | Design Build | FY27 Q3 | $25 – 50M | SB / Small Business | RFP1 / Competitive RFP - One Step | MILITARY SRM
567645 | Military | Hood FY26 Replacement JOC | Hood FY26 Replacement JOC | Fort Hood |  | MINIMUM GUARANTEE | Construction | Hired Labor - In House | 6 | Final Design | FY27 Q4 | < $1M | 8a / 8(a) | RFP1 / Competitive RFP - One Step | MILITARY SRM
568752 | Civil Works | EI City of Laredo Water Supply Infrastructure Improvements | WRDA 2024 Sec 1304, Webb County, Texas The estimated cost for an 8-inch waterline in Laredo is approximately $120 per foot, or $633,600 per mile of main. With $175 million, we could install 276 miles of replacement pipe | WEBB COUNTY, SECTION 219, TX |  | CONSTRUCTION CONTRACT | Construction |  |  |  | FY28 Q2 | $25 – 50M |  |  | CIVIL NonCAP
569894 | Environmental | AF Personnel Center-info mngt and strat. pln. spt. | New Task Order for Air Force Personnel Center that includes: Information Management Support, Project Management Support, and Strategic Planning Support | Joint Base San Antonio |  | FY26 OPY1 CONTRACT ACTIVITY | Services |  |  |  | FY26 Q3 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
570628 | Military | CAP 093384 Bliss Ready Building | Ready Building | Fort Bliss | Construction | CONSTRUCTION CONTRACT (SEE NOTEBOOK - GENERAL NOTES) | Construction | Design-Build, RFP developed by Hired Labor | 2 | Concept Design | FY28 Q2 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON CAPCES
570628 | Military | CAP 093384 Bliss Ready Building | Ready Building | Fort Bliss |  | AE CONTRACT - ENGINEERING SUPPORT | AE | Design-Build, RFP developed by Hired Labor | 2 | Concept Design | FY26 Q3 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON CAPCES
572918 | Military | Hood B90176 Hangar Door Expansion (HADES) | Expand hangar doors at Hangar B90176 | Fort Hood | Construction | CONSTRUCTION CONTRACT - # | Services | Architect-Engineer | 6 | Final Design | FY26 Q4 | $5 – 10M | SB / Small Business | IFB / Sealed Bid - Low Bid | MILITARY SRM
573506 | Environmental | EPA Sandy Beach Remediation | Provide remediation support to the EPA at the Sandy Beach site located in Tarrant County, TX |  |  | CONTRACT ACTIVITY | Services |  |  |  | FY27 Q2 | $5 – 10M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL NonDoD
573537 | Military | ACE MPLS239798 BMT RECRUIT DORMITORY 7 | BMT RECRUIT DORMITORY 7 | Lackland Air Force Base | AE | A-E TASK ORDER | AE | Architect-Engineer | 6 | Final Design | FY26 Q3 | $1 – 5M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MAJOR MILCON ACES
573537 | Military | ACE MPLS239798 BMT RECRUIT DORMITORY 7 | BMT RECRUIT DORMITORY 7 | Lackland Air Force Base | Construction | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY28 Q1 | > $250M | NONE / No set aside used | RFP1 / Competitive RFP - One Step | MAJOR MILCON ACES
573625 | IIS | DRT, LRT, RGV New Border Barrier RE Planning | Real Estate planning and Due Diligence including Title research, Metes and Bounds Survey and property Appraisal to enable future Land Acquisition effort. | Laredo, Tx |  | SWL-RE CONTRACTS | AE | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
574696 | Military | ACE TYMX200690 RAN MILITARY WORKING DOG KENNEL | 902 SFS CANINE KENNEL | Randolph Air Force Base | Construction | CONSTRUCTION CONTRACT | Construction | Architect-Engineer | 6 | Final Design | FY28 Q1 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON ACES
574696 | Military | ACE TYMX200690 RAN MILITARY WORKING DOG KENNEL | 902 SFS CANINE KENNEL | Randolph Air Force Base |  | AE CONTRACT | AE | Architect-Engineer | 6 | Final Design | FY26 Q4 | < $1M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MINOR MILCON ACES
574786 | Military | Polk - MAKS Army Airfield Upgrade (Construction) | Repair Taxiway C, Hoverlane C, Taxiway E, and Illuminated Signage. Repackage existing designs into 1 package, with base bid and options. Poject is construction portion from P2 566534 which is a PO unable to create DIV 00s. | Fort Polk |  | CONTRACT | Construction | Hired Labor - In House | 7 | Design Build | FY27 Q1 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | MILITARY SRM
574828 | IIS | Freer Border Patrol Station | Design and Construct Border Patrol Station for CBP in Freer, TX. | Laredo, Tx |  | CONTRACT | Construction | Hired Labor - In House |  |  | FY26 Q4 | $100 – 250M |  |  | IIS
574873 | Military | Bliss B745 Renovation and Repair (PTY) - Construction | Renovate and repair building 745 at Fort Bliss, TX. Includes DD1391 development and all other work necessary to make a complete and usable facility. | Fort Bliss |  | CONTRACT - # | Services | Design-Build, RFP developed by Hired Labor | 7 | Design Build | FY26 Q4 | $25 – 50M | SB / Small Business | RFP1 / Competitive RFP - One Step | MILITARY SRM
574874 | Military | Bliss Bird Netting B11291,92,93 & 94 - Construction | CON Project consists of the removal of bird habitats, bird droppings and deceased birds, as well as installation of bird abatement feature to keep birds from returning to dwell on the buildings B11291, B11292, B11293, & B11294. | Fort Bliss |  | CONTRACT - # | Construction | Architect-Engineer | 6 | Final Design | FY26 Q4 | $5 – 10M | SB / Small Business | RFP1 / Competitive RFP - One Step
575004 | Military | JBSA B16 Renovation Ph 2 (construction) | JBSA B16 Renovation Ph 2 (construction) | Fort Sam Houston | Construction | CONSTRUCTION CONTRACT | Services | Hired Labor - In House | 6 | Final Design | FY27 Q3 | $25 – 50M | SB / Small Business |  | MILITARY SRM
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | BBT-1 BOUNDARY SURVEY, MOSTLY HUDSPETH COUNTY | AE | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | MCS-EAST & WSL BOUNDARY SURVEYS, HIDALGO COUNTY | AE | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | PANSWD-26-P-0000 028782 BBT-3 BOUNDARY SURVEY, MOSTLY PRESIDIO COUNTY | AE | Technical Services |  |  | FY26 Q3 | $5 – 10M | NONE / No set aside used | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | REAL ESTATE CONTRACTS | Services | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | REVIEW & OVERSIGHT OF RGV, LRT & DRT SURVEYS | AE | Technical Services |  |  | FY26 Q3 | $5 – 10M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | RGC-EAST & MCS-WEST BOUNDARY SURVEY, STARR & HIDALGO COUNTIES | AE | Technical Services |  |  | FY26 Q3 | $5 – 10M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575092 | IIS | New Border Barrier RE Group A, DRT, LRT, RGV | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations and condemnation effort. | Laredo, Tx |  | RGC-WEST BOUNDARY SURVEY, STARR COUNTY | AE | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
575093 | IIS | SDC1 Marron Valley | Real Estate cradle to grave acquisition, including, metes and bounds survey, title research, appraisal, negotiations, and condemnation effort. | San Diego, Ca |  | REAL ESTATE CONTRACTS | Services | Technical Services |  |  | FY26 Q3 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | IIS
576184 | Environmental | Laughlin AFB IRP PFAS Soil Sampling for Drainage Project | Laughlin AFB IRP PFAS Soil Sampling for Drainage Project | Laughlin Air Force Base |  | CONTRACT ACTIVITY | Services |  |  |  | FY27 Q1 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
576373 | Environmental | FY26 BRAC Preaward S&R - LSAAP HEBG | FY26 Preaward S&R for LSAAP HEBG acquisition: excavation, sifting, removal and site closure. | Lone Star Army Ammo Plant |  | FY26 BASE CONTRACT ACTIVITY | Services |  |  |  | FY27 Q3 | $10 – 25M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
576405 | Environmental | Fort Chaffee CCL4 RIFS | Remedial Investigation (RI), Feasibility Study (FS), prepare Proposed Plan (PP), and Record of Decision (ROD) if required; additional groundwater sampling, of Carbon Tetrachloride (CCL4) in groundwater located at NE cantonment Installation. | Fort Chaffee |  | FY26 CONTRACT ACTIVITY | Services |  |  |  | FY26 Q4 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
576406 | Environmental | Fort Chaffee B460 RIFS | The overall objectives of this task order are to perform a Remedial Investigation (RI), perform a Feasibility Study (FS), prepare a Proposed Plan (PP), and prepare a Record of Decision (ROD) at Building 460. | Fort Chaffee |  | FY26 CONTRACT ACTIVITY | Services |  |  |  | FY26 Q4 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
576407 | Environmental | Fort Chaffee DMS/AR | This task order is to provide non-severable services for the development and implementation of records management system associated with the operation and environmental remediation. | Fort Chaffee |  | FY26 BASE CONTRACT ACTIVITY | Services |  |  |  | FY27 Q1 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
576807 | Environmental | Ecosystem and Natural Resource Range Study at Fort Stewart | CESU New agreement to implement the Fort Stewart Hunter Army Air Field Integrated Natural Resources Management Plan through habitat management, repair, reconfigure of lands, and GIS support. | Fort Stewart |  | FY26 BASE AGREEMENT CONTRACT | Services |  |  |  | FY26 Q3 | < $1M | NONE / No set aside used | OCM / Competitive Other Contracting Method | ENVIRONMENTAL DoD
577078 | Environmental | PBR for Exc.,Sift,&WasteDisposal-XXTest&SalvageYard | PWS provides env. remediation services at XX-Test Area and Salvage Yard area at LSAAP, TX. PWS defines scope of performance-based env. remediation activities to achieve Progress towards Remedy Standard B in accordance with TCEQ permits. | Lone Star Army Ammo Plant |  | FY26 CONTRACT ACTIVITY | Services |  |  |  | FY27 Q1 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
577318 | Environmental | HEDG Transect Investigation, LSAAP | Determine the presence or absence of MEC and MD. The scope includes performing transects using DGM from the boundary of the HEDG operating unit to 2000 feet out to determine the full extent of munitions. | Red River Army Depot |  | FY26 BASE CONTRACT ACTIVITY | Services |  |  |  | FY27 Q1 | < $1M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD
577743 | Environmental | AFCEC Land Management Mapping | CESU: to collect, analyze, and apply Environmental, Natural and Cultural Resource Data to Implement Land Rehabilitation and Maintenance for Optimal Management of Public Lands Under Control of the Department of the Air Force (DAF). | San Antonio Air Force Station |  | FY26 BASE AGREEMENT CONTRACT *SEE NOTEBOOK TAB* | Services |  |  |  | FY26 Q3 | $5 – 10M | NONE / No set aside used | OCM / Competitive Other Contracting Method | ENVIRONMENTAL DoD
578007 | IIS | Sierra Delta | Real Estate cradle to grave acquisition of one partial property in Nogales, AZ for border access and infrastructure, including metes and bounds survey, title research, appraisal, negotiations, potential condemnation effort, and closing | Tucson, Az |  | REAL ESTATE CONTRACT | Services | Technical Services |  |  | FY26 Q3 | < $1M |  |  | IIS
578921 | Environmental | AMC P2AO (Redstone Arsenal) | This project entails conducting a Pollution prevention Opportunity Assessment for the Industrial Areas (SIA) at TDAAPs. | Redstone Arsenal |  | CONTRACT ACTIVITY | Services |  |  |  | FY26 Q4 | $1 – 5M | SB / Small Business | IDC / Competitive DO/TO against existing contract (Definite-quantity, Requirements, or Indefinite-quantity contracts) | ENVIRONMENTAL DoD